## Checklist
Concrete Pouring SOP checklist
SOP-CON-006 ¦ Rev 1.0 ¦ Owner: Site Supervisor
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Inspect formwork and reinforcement | Before ordering concrete, the quality inspector checks formwork alignment, bracing and cleanliness, and confirms reinforcement placement, cover and tie-off match the drawings, then signs off the pour. Checkpoint: The pour does not start until formwork and reinforcement are signed off against the drawings. | Quality Inspector
5.2 | Schedule the concrete delivery | Confirm the mix design, quantity and pour sequence with the supplier, and schedule the pump or chute and crew to arrive together with the first truck. | Site Supervisor
5.3 | Check the delivery ticket and slump on arrival | On arrival, check the delivery ticket against the ordered mix design and batch time, then perform a slump test and reject the load if it falls outside the accepted range. Warning: Never add water on site to adjust slump beyond what the mix design and supplier allow. | Quality Inspector
5.4 | Position the pump or chute | Set up the pump line or chute to reach the pour area safely, keeping the discharge point close to its final position to reduce the drop and movement of wet concrete. | Pump Operator
5.5 | Place concrete in sequence | Place concrete in the planned sequence and in layers, keeping the discharge point close to its final resting place and avoiding dropping or dragging it long distances that could cause segregation. | Concrete Crew
5.6 | Consolidate with a vibrator | Insert the vibrator vertically at regular intervals into each layer, holding it long enough to release trapped air without over-vibrating, and avoid contact with reinforcement or formwork. | Concrete Crew
5.7 | Screed and level the surface | Strike off excess concrete with a screed board guided by the formwork edges or screed rails to bring the surface to the correct level and slope. | Concrete Crew
5.8 | Finish the surface | Float and trowel the surface to the specified finish once bleed water has evaporated, timing the finishing to avoid trapping water or damaging the surface. Checkpoint: Finishing starts only after surface bleed water has disappeared. | Concrete Crew
5.9 | Apply curing measures | Apply curing compound, cover with curing blankets, or keep the surface continuously moist as soon as the finish allows, protecting it from rapid drying, wind and temperature extremes. | Concrete Crew
5.10 | Maintain curing for the required period | Keep the curing method in place for the period set by the mix design or project specification, checking coverings periodically to confirm they remain intact. | Site Supervisor
5.11 | Approve formwork stripping | Confirm the concrete has reached the strength required for stripping, based on test cylinder results or the specified time, before authorizing formwork removal. | Quality Inspector
5.12 | Clean up and record the pour | Wash down equipment away from drains in a designated washout area, and record the pour date, quantity, mix design, slump result and any issues in the site log. | Site Supervisor
Supervisor sign-off: |  |  | Date:

## SOP
Concrete Pouring SOP
Standard operating procedure
Document no. | SOP-CON-006
Revision | 1.0
Owner | Site Supervisor
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To make sure concrete is placed, consolidated, finished and cured correctly so the finished structure meets the design strength, tolerance and surface requirements.
2. Scope
Applies to all concrete pours on the construction site, from formwork inspection through placement, finishing and curing, for slabs, footings and structural elements.
Definitions
Slump test | A field test measuring the consistency of fresh concrete to check it matches the ordered mix design before placement.
Segregation | Separation of the coarse aggregate from the cement paste during placement, which weakens the finished concrete.
Curing | Keeping placed concrete moist and at a suitable temperature for a set period so it gains strength properly.
3. Responsibilities
Concrete Crew | Places, consolidates and finishes the concrete, and applies curing measures after finishing.
Site Supervisor | Confirms formwork and reinforcement sign-off, schedules the pour and coordinates the delivery and pump.
Quality Inspector | Inspects formwork and reinforcement before the pour, tests delivered concrete, and verifies curing and stripping timing.
Pump Operator | Positions and operates the concrete pump or chute safely and controls the flow rate during placement.
RACI matrix
Inspect formwork and reinforcement before pour | Concrete Crew: I ¦ Site Supervisor: A ¦ Quality Inspector: R ¦ Pump Operator: -
Test delivered concrete on arrival | Concrete Crew: C ¦ Site Supervisor: I ¦ Quality Inspector: R/A ¦ Pump Operator: I
Place and consolidate concrete | Concrete Crew: R/A ¦ Site Supervisor: I ¦ Quality Inspector: C ¦ Pump Operator: R
Finish and cure the surface | Concrete Crew: R/A ¦ Site Supervisor: I ¦ Quality Inspector: C ¦ Pump Operator: -
Approve formwork stripping | Concrete Crew: I ¦ Site Supervisor: C ¦ Quality Inspector: R/A ¦ Pump Operator: -
4. Materials and PPE
Materials, tools and systems
Approved concrete mix design and delivery ticket
Slump test cone and testing kit
Concrete pump, chute or bucket
Vibrator for consolidation
Screed board and finishing tools (float, trowel)
Curing compound or curing blankets and plastic sheeting
Formwork and reinforcement inspection checklist
Personal protective equipment
Hard hat
Safety glasses
Rubber boots resistant to wet concrete
Chemical-resistant gloves
High-visibility vest
5. Procedure
5.1 Inspect formwork and reinforcement | Before ordering concrete, the quality inspector checks formwork alignment, bracing and cleanliness, and confirms reinforcement placement, cover and tie-off match the drawings, then signs off the pour. Owner: Quality Inspector Checkpoint: The pour does not start until formwork and reinforcement are signed off against the drawings.
5.2 Schedule the concrete delivery | Confirm the mix design, quantity and pour sequence with the supplier, and schedule the pump or chute and crew to arrive together with the first truck. Owner: Site Supervisor
5.3 Check the delivery ticket and slump on arrival | On arrival, check the delivery ticket against the ordered mix design and batch time, then perform a slump test and reject the load if it falls outside the accepted range. Owner: Quality Inspector Warning: Never add water on site to adjust slump beyond what the mix design and supplier allow.
5.4 Position the pump or chute | Set up the pump line or chute to reach the pour area safely, keeping the discharge point close to its final position to reduce the drop and movement of wet concrete. Owner: Pump Operator
5.5 Place concrete in sequence | Place concrete in the planned sequence and in layers, keeping the discharge point close to its final resting place and avoiding dropping or dragging it long distances that could cause segregation. Owner: Concrete Crew
5.6 Consolidate with a vibrator | Insert the vibrator vertically at regular intervals into each layer, holding it long enough to release trapped air without over-vibrating, and avoid contact with reinforcement or formwork. Owner: Concrete Crew
5.7 Screed and level the surface | Strike off excess concrete with a screed board guided by the formwork edges or screed rails to bring the surface to the correct level and slope. Owner: Concrete Crew
5.8 Finish the surface | Float and trowel the surface to the specified finish once bleed water has evaporated, timing the finishing to avoid trapping water or damaging the surface. Owner: Concrete Crew Checkpoint: Finishing starts only after surface bleed water has disappeared.
5.9 Apply curing measures | Apply curing compound, cover with curing blankets, or keep the surface continuously moist as soon as the finish allows, protecting it from rapid drying, wind and temperature extremes. Owner: Concrete Crew
5.10 Maintain curing for the required period | Keep the curing method in place for the period set by the mix design or project specification, checking coverings periodically to confirm they remain intact. Owner: Site Supervisor
5.11 Approve formwork stripping | Confirm the concrete has reached the strength required for stripping, based on test cylinder results or the specified time, before authorizing formwork removal. Owner: Quality Inspector
5.12 Clean up and record the pour | Wash down equipment away from drains in a designated washout area, and record the pour date, quantity, mix design, slump result and any issues in the site log. Owner: Site Supervisor
6. Quality checks
Formwork and reinforcement are signed off against the drawings before every pour.
Slump test results are recorded for every truck and fall within the accepted range.
Test cylinders are taken and cured for strength testing on structural pours.
Curing measures remain in place for the full period specified for the mix.
Formwork is not stripped before the concrete reaches the required strength.
7. Records
Delivery tickets and slump test results
Formwork and reinforcement inspection sign-off
Test cylinder records and strength results
Pour log with date, quantity and issues noted
8. KPIs
Percentage of loads accepted on first slump test
Number of formwork or reinforcement rejections before pour
Average time between finishing and curing application
9. Common mistakes
Adding water on site to make a stiff load easier to place.
Starting to trowel before bleed water has left the surface.
Skipping curing measures because the crew is in a hurry to move on.
Stripping formwork before test results confirm the concrete has reached strength.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Ilia Pirozhenko

## Training Log
Concrete Pouring SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Concrete Pouring SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Ilia Pirozhenko

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.