## Checklist
Daily Construction Site Report SOP checklist
SOP-CON-007 ¦ Rev 1.0 ¦ Owner: Site Supervisor
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Record weather and site conditions | At the start of the shift, record the weather conditions, temperature and any site condition such as standing water or ground closures that could affect work. | Site Supervisor
5.2 | Log manpower on site | Collect headcount by trade and subcontractor from each foreman, and record it against the crew planned for that day in the daily report. | Subcontractor Foreman
5.3 | Log equipment on site | Record major equipment present on site that day, such as cranes, excavators and generators, including hours used if tracked for the project. | Site Supervisor
5.4 | Log deliveries and materials received | Record materials and deliveries received during the shift against delivery tickets, noting the supplier, quantity and any damage or shortage found on arrival. | Site Supervisor
5.5 | Record work performed and progress | Describe the specific work completed by each trade that day and compare it against the project schedule, noting whether the work is ahead, on track or behind. Checkpoint: Progress recorded in the report is compared against the current project schedule, not just described in isolation. | Site Supervisor
5.6 | Log delays and issues | Record any delay event such as weather, missing materials, a design query or access restriction, including the time it started and its estimated impact on the schedule. Warning: Record delay events the same day, since a late or missing entry can weaken a schedule claim later. | Site Supervisor
5.7 | Record safety observations | Note any safety observation, near miss or incident that occurred during the shift, cross-referencing the separate incident report if one was filed. | Site Supervisor
5.8 | Take site photos | Take dated photos of key progress areas, any delay condition and any damage or defect noted, and attach them to the daily report. | Site Supervisor
5.9 | Get subcontractor sign-off | Have each subcontractor foreman review the manpower, equipment and progress entries for their crew and confirm they are accurate before the report is submitted. Checkpoint: Every subcontractor foreman confirms their crew's entries before the report is submitted. | Subcontractor Foreman
5.10 | Submit the report | Submit the completed daily report to the project manager before the end of the site supervisor's shift. | Site Supervisor
5.11 | Review and follow up | Review the report for delay events or issues needing client, design or procurement input, and assign follow-up actions with an owner and due date. | Project Manager
5.12 | File and archive the report | File the signed daily report and its photos in the project record system so it can be retrieved for schedule reviews or claims. | Site Clerk
Supervisor sign-off: |  |  | Date:

## SOP
Daily Construction Site Report SOP
Standard operating procedure
Document no. | SOP-CON-007
Revision | 1.0
Owner | Site Supervisor
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To create an accurate, same-day written record of site conditions, manpower, progress, deliveries and issues that project stakeholders can rely on and refer back to.
2. Scope
Applies to daily reporting on all active construction site work, covering every trade and subcontractor working on site that day.
Definitions
Daily site report | A same-day written record of weather, manpower, equipment, progress, deliveries and issues on a construction site.
Delay event | Any occurrence that stops or slows planned work, such as weather, missing materials or a design query.
3. Responsibilities
Site Supervisor | Compiles the daily report from field observations and subcontractor input, and submits it by the end of shift.
Subcontractor Foreman | Provides accurate manpower, equipment and progress information for their crew and reviews the report before sign-off.
Project Manager | Reviews daily reports for delays and issues, and follows up on items needing client or design input.
Site Clerk | Files and archives completed reports and compiles them for weekly progress meetings.
RACI matrix
Record weather and site conditions | Site Supervisor: R/A ¦ Subcontractor Foreman: I ¦ Project Manager: I ¦ Site Clerk: -
Log manpower and equipment on site | Site Supervisor: A ¦ Subcontractor Foreman: R ¦ Project Manager: I ¦ Site Clerk: -
Record progress and delay events | Site Supervisor: R/A ¦ Subcontractor Foreman: C ¦ Project Manager: I ¦ Site Clerk: -
Submit and file the daily report | Site Supervisor: R ¦ Subcontractor Foreman: I ¦ Project Manager: A ¦ Site Clerk: R
Follow up on delay events | Site Supervisor: R ¦ Subcontractor Foreman: C ¦ Project Manager: A ¦ Site Clerk: I
4. Materials and PPE
Materials, tools and systems
Daily site report form or app
Site diary or logbook
Camera or phone for site photos
Weather reference (thermometer or forecast source)
Delivery tickets and material receipts
Project schedule for progress comparison
Personal protective equipment
Hard hat
High-visibility vest
Safety boots
5. Procedure
5.1 Record weather and site conditions | At the start of the shift, record the weather conditions, temperature and any site condition such as standing water or ground closures that could affect work. Owner: Site Supervisor
5.2 Log manpower on site | Collect headcount by trade and subcontractor from each foreman, and record it against the crew planned for that day in the daily report. Owner: Subcontractor Foreman
5.3 Log equipment on site | Record major equipment present on site that day, such as cranes, excavators and generators, including hours used if tracked for the project. Owner: Site Supervisor
5.4 Log deliveries and materials received | Record materials and deliveries received during the shift against delivery tickets, noting the supplier, quantity and any damage or shortage found on arrival. Owner: Site Supervisor
5.5 Record work performed and progress | Describe the specific work completed by each trade that day and compare it against the project schedule, noting whether the work is ahead, on track or behind. Owner: Site Supervisor Checkpoint: Progress recorded in the report is compared against the current project schedule, not just described in isolation.
5.6 Log delays and issues | Record any delay event such as weather, missing materials, a design query or access restriction, including the time it started and its estimated impact on the schedule. Owner: Site Supervisor Warning: Record delay events the same day, since a late or missing entry can weaken a schedule claim later.
5.7 Record safety observations | Note any safety observation, near miss or incident that occurred during the shift, cross-referencing the separate incident report if one was filed. Owner: Site Supervisor
5.8 Take site photos | Take dated photos of key progress areas, any delay condition and any damage or defect noted, and attach them to the daily report. Owner: Site Supervisor
5.9 Get subcontractor sign-off | Have each subcontractor foreman review the manpower, equipment and progress entries for their crew and confirm they are accurate before the report is submitted. Owner: Subcontractor Foreman Checkpoint: Every subcontractor foreman confirms their crew's entries before the report is submitted.
5.10 Submit the report | Submit the completed daily report to the project manager before the end of the site supervisor's shift. Owner: Site Supervisor
5.11 Review and follow up | Review the report for delay events or issues needing client, design or procurement input, and assign follow-up actions with an owner and due date. Owner: Project Manager
5.12 File and archive the report | File the signed daily report and its photos in the project record system so it can be retrieved for schedule reviews or claims. Owner: Site Clerk
6. Quality checks
A daily report exists for every working day on the project, with no gaps.
Manpower and equipment entries are confirmed by the relevant subcontractor foreman.
Delay events include a start time and estimated schedule impact.
Reports are submitted the same day rather than backdated later.
7. Records
Signed daily site reports
Site photos by date
Delivery tickets and material receipts
Delay event log
8. KPIs
Percentage of working days with a same-day daily report filed
Number of delay events logged per month
Average time between shift end and report submission
9. Common mistakes
Writing vague progress notes that cannot be compared against the schedule.
Forgetting to log a delay event until days later.
Skipping subcontractor sign-off on manpower and progress entries.
Not attaching photos of delay conditions or defects when they occur.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Ilia Pirozhenko

## Training Log
Daily Construction Site Report SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Daily Construction Site Report SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Ilia Pirozhenko

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.