## Checklist
Excavation and Trenching SOP checklist
SOP-CON-003 ¦ Rev 1.0 ¦ Owner: Excavation Competent Person
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Request the excavation permit | The site supervisor requests an excavation permit before any digging starts, describing the location, depth and duration of the planned work. | Site Supervisor
5.2 | Complete utility locates | Request underground utility locates and confirm all marked utilities are identified and, where required, verified by hand digging or another safe method before machine excavation begins. Warning: Never excavate near an unmarked or unconfirmed utility line. | Site Supervisor
5.3 | Classify the soil and choose a protective system | The competent person classifies the soil type and selects sloping, benching, shoring or a shield sized for the depth and conditions, following the manufacturer's tabulated data or a registered engineer's design. | Excavation Competent Person
5.4 | Set up barricades and signage | Install barricades, fencing and warning signs around the full perimeter of the excavation before it is left open or unattended, including at night. | Laborer
5.5 | Position spoil and equipment safely | Place excavated spoil, materials and equipment back from the edge of the excavation by the setback distance required by the protective system design or local regulations. | Equipment Operator
5.6 | Provide safe access and egress | Install a ladder, ramp or stairway within the excavation so that no worker has to travel an excessive lateral distance to exit, positioned within the protected zone. | Excavation Competent Person
5.7 | Test the atmosphere in deep excavations | For deep or confined excavations, test the atmosphere for oxygen level and hazardous gases with a calibrated monitor before entry and at intervals during the work. | Excavation Competent Person
5.8 | Inspect before entry each day | The competent person inspects the excavation, protective system, access and surrounding ground at the start of each shift and after any rainfall, vibration or other event that could increase hazards. Checkpoint: No worker enters the excavation until the competent person has signed off that day's inspection. | Excavation Competent Person
5.9 | Work within the protective system | Workers stay within the sloped, benched or shielded area at all times while in the excavation, and do not work under suspended loads or unsupported sections. | Laborer
5.10 | Stop work if conditions change | Anyone who notices water accumulation, cracking, slumping soil or an unexpected utility must stop work, exit the excavation and notify the competent person immediately. Checkpoint: Work stops immediately if any sign of instability is observed. | Laborer
5.11 | Backfill and reinstate | Backfill the excavation in the sequence and compaction specified in the design, removing the protective system in a controlled manner as backfilling progresses. | Equipment Operator
5.12 | Close out the permit | Confirm the excavation is backfilled, barricades removed and the area reinstated, then sign off and file the completed excavation permit and inspection log. | Site Supervisor
Supervisor sign-off: |  |  | Date:

## SOP
Excavation and Trenching SOP
Standard operating procedure
Document no. | SOP-CON-003
Revision | 1.0
Owner | Excavation Competent Person
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To prevent cave-ins, utility strikes and falls by requiring a permit, a protective system and a competent-person inspection before anyone enters an excavation or trench.
2. Scope
Applies to all excavation and trenching work on the construction site, including utility trenches, foundation excavations and pits of any depth requiring worker entry.
Definitions
Competent person | A person trained and authorized to classify soil, select protective systems and inspect excavations, and who can stop work if a hazard is identified.
Protective system | Sloping, benching, shoring or a shield (trench box) used to protect workers from a cave-in.
Spoil pile | Excavated soil or material stacked beside the excavation, which must be set back from the edge.
Utility locate | The process of marking or confirming the position of underground utilities before digging begins.
3. Responsibilities
Excavation Competent Person | Classifies soil, selects the protective system, inspects the excavation daily and can stop entry if conditions are unsafe.
Equipment Operator | Operates excavation machinery, follows the competent person's instructions and watches for utility markers and spotters.
Laborer | Works in or near the excavation following the protective system and access rules, and reports hazards immediately.
Site Supervisor | Confirms the permit is in place, coordinates utility locates and enforces the exclusion zone around the excavation.
RACI matrix
Obtain permit and utility locates | Excavation Competent Person: C ¦ Equipment Operator: I ¦ Laborer: I ¦ Site Supervisor: R/A
Classify soil and select protective system | Excavation Competent Person: R/A ¦ Equipment Operator: I ¦ Laborer: I ¦ Site Supervisor: C
Inspect excavation before entry each day | Excavation Competent Person: R/A ¦ Equipment Operator: I ¦ Laborer: I ¦ Site Supervisor: I
Maintain barricades and signage | Excavation Competent Person: C ¦ Equipment Operator: - ¦ Laborer: R ¦ Site Supervisor: A
Stop work if a hazard is found | Excavation Competent Person: R/A ¦ Equipment Operator: R ¦ Laborer: R ¦ Site Supervisor: A
4. Materials and PPE
Materials, tools and systems
Excavation permit form
Utility locate request and markings
Protective system: shoring, trench box or sloping equipment
Ladder or ramp rated for safe access and egress
Barricades, fencing and warning signage
Atmospheric gas monitor for deep or confined excavations
Daily excavation inspection log
Personal protective equipment
Hard hat
High-visibility vest
Safety boots with toe protection
Safety glasses
Gloves
5. Procedure
5.1 Request the excavation permit | The site supervisor requests an excavation permit before any digging starts, describing the location, depth and duration of the planned work. Owner: Site Supervisor
5.2 Complete utility locates | Request underground utility locates and confirm all marked utilities are identified and, where required, verified by hand digging or another safe method before machine excavation begins. Owner: Site Supervisor Warning: Never excavate near an unmarked or unconfirmed utility line.
5.3 Classify the soil and choose a protective system | The competent person classifies the soil type and selects sloping, benching, shoring or a shield sized for the depth and conditions, following the manufacturer's tabulated data or a registered engineer's design. Owner: Excavation Competent Person
5.4 Set up barricades and signage | Install barricades, fencing and warning signs around the full perimeter of the excavation before it is left open or unattended, including at night. Owner: Laborer
5.5 Position spoil and equipment safely | Place excavated spoil, materials and equipment back from the edge of the excavation by the setback distance required by the protective system design or local regulations. Owner: Equipment Operator
5.6 Provide safe access and egress | Install a ladder, ramp or stairway within the excavation so that no worker has to travel an excessive lateral distance to exit, positioned within the protected zone. Owner: Excavation Competent Person
5.7 Test the atmosphere in deep excavations | For deep or confined excavations, test the atmosphere for oxygen level and hazardous gases with a calibrated monitor before entry and at intervals during the work. Owner: Excavation Competent Person
5.8 Inspect before entry each day | The competent person inspects the excavation, protective system, access and surrounding ground at the start of each shift and after any rainfall, vibration or other event that could increase hazards. Owner: Excavation Competent Person Checkpoint: No worker enters the excavation until the competent person has signed off that day's inspection.
5.9 Work within the protective system | Workers stay within the sloped, benched or shielded area at all times while in the excavation, and do not work under suspended loads or unsupported sections. Owner: Laborer
5.10 Stop work if conditions change | Anyone who notices water accumulation, cracking, slumping soil or an unexpected utility must stop work, exit the excavation and notify the competent person immediately. Owner: Laborer Checkpoint: Work stops immediately if any sign of instability is observed.
5.11 Backfill and reinstate | Backfill the excavation in the sequence and compaction specified in the design, removing the protective system in a controlled manner as backfilling progresses. Owner: Equipment Operator
5.12 Close out the permit | Confirm the excavation is backfilled, barricades removed and the area reinstated, then sign off and file the completed excavation permit and inspection log. Owner: Site Supervisor
6. Quality checks
No excavation permit is issued without confirmed utility locates on file.
Every excavation has a documented soil classification and matching protective system.
Daily inspection log entries exist for every day the excavation remained open.
Spoil and equipment are kept back from the edge by the required setback distance.
7. Records
Excavation permit
Utility locate confirmation
Daily excavation inspection log
Soil classification and protective system design
8. KPIs
Percentage of excavations with a same-day inspection log entry
Number of stop-work events related to excavation hazards
Utility strikes per year
9. Common mistakes
Entering an excavation before the competent person's daily inspection.
Piling spoil or parking equipment too close to the excavation edge.
Skipping a protective system for a trench assumed to be shallow enough.
Not re-inspecting after rain or nearby vibration from equipment.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Ilia Pirozhenko

## Training Log
Excavation and Trenching SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Excavation and Trenching SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Ilia Pirozhenko

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.