## Checklist
Event Planning SOP checklist
SOP-EVT-001 ¦ Rev 1.0 ¦ Owner: Event Manager
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Capture the client brief | Meet with the client to capture the event goals, date, guest count, budget range and any must-have elements, recording it all in the client brief template. | Event Coordinator
5.2 | Confirm venue availability | Check venue availability for the requested date and capacity, and hold the space with a deposit or option per the venue's policy. | Event Coordinator
5.3 | Build the initial budget | Build a line-item budget covering venue, catering, decor, entertainment and staffing, and share it with the client for approval before booking anything. Checkpoint: The client approves the budget before any vendor deposits are paid. | Event Coordinator
5.4 | Create the production schedule | Build a production schedule showing every planning task, deposit due date and vendor booking deadline between now and event day. | Event Coordinator
5.5 | Select and book vendors | Request quotes from vendors for each service needed, compare them against the budget, and book the selected vendors following the vendor coordination SOP. | Event Coordinator
5.6 | Confirm the venue floor plan | Finalize the floor plan with the venue, including seating layout, staging, and any load-in or accessibility considerations. | Event Coordinator
5.7 | Track deposits and payments | Track vendor deposits and payment due dates against the production schedule, confirming each payment is made on time to hold bookings. Warning: A missed vendor deposit deadline can cause a booking to be released to another client. | Event Coordinator
5.8 | Update the client regularly | Send the client a planning update at each major milestone, such as vendor confirmations or floor plan approval, rather than waiting until questions arise. | Event Coordinator
5.9 | Build the event day run sheet | Build the detailed, timed run sheet covering setup, guest arrival, program flow and breakdown, using vendor confirmations to set accurate timing. | Event Coordinator
5.10 | Confirm final guest count and details | Confirm the final guest count, dietary requirements and any last changes with the client by the vendor's final headcount deadline. Checkpoint: Final guest count is confirmed with the client before the caterer's final headcount deadline. | Event Coordinator
5.11 | Hold the pre-event review | Review the run sheet, floor plan and vendor confirmations with the event manager before event day to catch any gaps. | Event Manager
5.12 | Distribute the final plan | Send the finalized run sheet and floor plan to all vendors, venue staff and the client ahead of event day so everyone is working from the same plan. | Event Coordinator
Supervisor sign-off: |  |  | Date:

## SOP
Event Planning SOP
Standard operating procedure
Document no. | SOP-EVT-001
Revision | 1.0
Owner | Event Manager
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To plan events consistently from brief to execution, so nothing is missed on budget, timeline or vendor coordination before event day.
2. Scope
Applies to event coordinators planning corporate, social or private events from the initial client brief through the pre-event review. Day-of execution and vendor coordination have their own dedicated SOPs.
Definitions
Client brief | The initial document capturing the client's event goals, guest count, date, budget range and key preferences.
Run sheet | The detailed, timed schedule of everything that must happen on event day, used during execution.
Production schedule | The planning timeline showing when each planning task, deposit and vendor booking is due before the event.
3. Responsibilities
Event Coordinator | Builds the timeline and budget, books vendors, and keeps the client updated throughout planning.
Event Manager | Approves the budget and contracts, and signs off on the plan before it moves to execution.
Client | Approves the brief, budget and key decisions, and provides timely feedback during planning.
RACI matrix
Capture the client brief | Event Coordinator: R/A ¦ Event Manager: I ¦ Client: C
Build the budget and timeline | Event Coordinator: R ¦ Event Manager: A ¦ Client: C
Book and contract vendors | Event Coordinator: R ¦ Event Manager: A ¦ Client: I
Approve the final event plan | Event Coordinator: R ¦ Event Manager: A ¦ Client: A
4. Materials and PPE
Materials, tools and systems
Client brief template
Event budget spreadsheet
Production schedule or planning timeline
Vendor contact and contract tracker
Venue floor plan
Run sheet template
5. Procedure
5.1 Capture the client brief | Meet with the client to capture the event goals, date, guest count, budget range and any must-have elements, recording it all in the client brief template. Owner: Event Coordinator
5.2 Confirm venue availability | Check venue availability for the requested date and capacity, and hold the space with a deposit or option per the venue's policy. Owner: Event Coordinator
5.3 Build the initial budget | Build a line-item budget covering venue, catering, decor, entertainment and staffing, and share it with the client for approval before booking anything. Owner: Event Coordinator Checkpoint: The client approves the budget before any vendor deposits are paid.
5.4 Create the production schedule | Build a production schedule showing every planning task, deposit due date and vendor booking deadline between now and event day. Owner: Event Coordinator
5.5 Select and book vendors | Request quotes from vendors for each service needed, compare them against the budget, and book the selected vendors following the vendor coordination SOP. Owner: Event Coordinator
5.6 Confirm the venue floor plan | Finalize the floor plan with the venue, including seating layout, staging, and any load-in or accessibility considerations. Owner: Event Coordinator
5.7 Track deposits and payments | Track vendor deposits and payment due dates against the production schedule, confirming each payment is made on time to hold bookings. Owner: Event Coordinator Warning: A missed vendor deposit deadline can cause a booking to be released to another client.
5.8 Update the client regularly | Send the client a planning update at each major milestone, such as vendor confirmations or floor plan approval, rather than waiting until questions arise. Owner: Event Coordinator
5.9 Build the event day run sheet | Build the detailed, timed run sheet covering setup, guest arrival, program flow and breakdown, using vendor confirmations to set accurate timing. Owner: Event Coordinator
5.10 Confirm final guest count and details | Confirm the final guest count, dietary requirements and any last changes with the client by the vendor's final headcount deadline. Owner: Event Coordinator Checkpoint: Final guest count is confirmed with the client before the caterer's final headcount deadline.
5.11 Hold the pre-event review | Review the run sheet, floor plan and vendor confirmations with the event manager before event day to catch any gaps. Owner: Event Manager
5.12 Distribute the final plan | Send the finalized run sheet and floor plan to all vendors, venue staff and the client ahead of event day so everyone is working from the same plan. Owner: Event Coordinator
6. Quality checks
The client approves the budget before any vendor deposits are paid.
Every vendor booking on the production schedule has a signed contract on file.
Final guest count is confirmed before the caterer's headcount deadline.
The pre-event review is completed before the run sheet is distributed.
7. Records
Client brief
Approved event budget
Production schedule
Signed vendor contracts
Final run sheet
8. KPIs
Percentage of events planned within the approved budget
Vendor booking deadlines met on schedule
Time from brief to first budget approval
Client satisfaction score after the event
9. Common mistakes
Booking a vendor before the client approves the budget.
Missing a vendor deposit deadline and losing the booking.
Building the run sheet without confirmed vendor timing.
Confirming the final guest count after the caterer's deadline.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Alexa Uskova

## Training Log
Event Planning SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Event Planning SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Alexa Uskova

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.