## Checklist
Event Vendor Coordination SOP checklist
SOP-EVT-003 ¦ Rev 1.0 ¦ Owner: Event Manager
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Identify vendor needs | Review the event budget and brief to identify which vendor categories are needed, such as catering, decor, entertainment or AV. | Event Coordinator
5.2 | Source and shortlist vendors | Check the preferred vendor list first, and source additional quotes from outside vendors when needed, comparing at least two or three options per category. | Event Coordinator
5.3 | Request and compare quotes | Request an itemized quote from each shortlisted vendor covering the same scope of work, so pricing and deliverables can be compared fairly. | Event Coordinator
5.4 | Confirm scope of work in writing | Document the agreed scope of work with each selected vendor, including deliverables, timing, headcount if relevant, and cancellation terms. Checkpoint: Every selected vendor has a written scope of work before a contract is signed. | Event Coordinator
5.5 | Get contracts approved and signed | Route each vendor contract to the event manager for approval, and get it signed by both parties before paying any deposit. Warning: Never pay a vendor deposit against an unsigned contract. | Event Manager
5.6 | Track deposits and payment schedule | Record each vendor's deposit and remaining balance due dates in the payment tracker, and confirm payments are made on schedule. | Event Coordinator
5.7 | Schedule load-in windows | Coordinate with the venue manager to assign each vendor a load-in time window that avoids conflicts with other vendors and the venue's own schedule. Checkpoint: No two vendors are scheduled the same load-in window in a space that cannot fit both at once. | Event Coordinator
5.8 | Confirm details before the event | Contact each vendor about a week before the event to reconfirm timing, final headcount or quantities, and any last details. | Event Coordinator
5.9 | Share the run sheet with vendors | Send each vendor the relevant sections of the event run sheet so they know their cues and timing on event day. | Event Coordinator
5.10 | Manage vendor issues on event day | Address vendor delays, substitutions or scope issues on event day by working with the event lead, following the event day run of show SOP. | Event Coordinator
5.11 | Process final payments | Confirm the vendor delivered per the scope of work before releasing the final payment, noting any shortfall before paying in full. | Event Manager
5.12 | Review vendor performance | Complete a vendor performance review after the event covering reliability, quality and communication, and update the preferred vendor list accordingly. | Event Coordinator
Supervisor sign-off: |  |  | Date:

## SOP
Event Vendor Coordination SOP
Standard operating procedure
Document no. | SOP-EVT-003
Revision | 1.0
Owner | Event Manager
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To select reliable vendors, formalize agreements clearly, and coordinate their work so every vendor arrives on time and delivers what was contracted.
2. Scope
Applies to event coordinators sourcing and managing vendors such as catering, decor, entertainment and AV for an event. Day-of cue calling is covered by the event day run of show SOP.
Definitions
Vendor scope of work | The specific services, deliverables and timing a vendor is contracted to provide for the event.
Load-in window | The scheduled time slot a vendor has to bring in and set up their equipment or materials.
Preferred vendor list | The list of vendors a venue or company has vetted and recommends for use at their events.
3. Responsibilities
Event Coordinator | Sources vendors, negotiates scope, schedules load-in windows, and manages day-to-day vendor communication.
Event Manager | Approves vendor contracts and payments, and resolves vendor performance issues.
Venue Manager | Approves vendor load-in access and enforces venue rules for outside vendors.
RACI matrix
Source and shortlist vendors | Event Coordinator: R/A ¦ Event Manager: C ¦ Venue Manager: I
Approve vendor contracts | Event Coordinator: R ¦ Event Manager: A ¦ Venue Manager: I
Schedule load-in windows | Event Coordinator: R ¦ Event Manager: I ¦ Venue Manager: A
Review vendor performance after the event | Event Coordinator: R ¦ Event Manager: A ¦ Venue Manager: C
4. Materials and PPE
Materials, tools and systems
Preferred vendor list
Vendor scope of work template
Vendor contract template
Load-in schedule
Vendor payment tracker
Vendor performance review form
5. Procedure
5.1 Identify vendor needs | Review the event budget and brief to identify which vendor categories are needed, such as catering, decor, entertainment or AV. Owner: Event Coordinator
5.2 Source and shortlist vendors | Check the preferred vendor list first, and source additional quotes from outside vendors when needed, comparing at least two or three options per category. Owner: Event Coordinator
5.3 Request and compare quotes | Request an itemized quote from each shortlisted vendor covering the same scope of work, so pricing and deliverables can be compared fairly. Owner: Event Coordinator
5.4 Confirm scope of work in writing | Document the agreed scope of work with each selected vendor, including deliverables, timing, headcount if relevant, and cancellation terms. Owner: Event Coordinator Checkpoint: Every selected vendor has a written scope of work before a contract is signed.
5.5 Get contracts approved and signed | Route each vendor contract to the event manager for approval, and get it signed by both parties before paying any deposit. Owner: Event Manager Warning: Never pay a vendor deposit against an unsigned contract.
5.6 Track deposits and payment schedule | Record each vendor's deposit and remaining balance due dates in the payment tracker, and confirm payments are made on schedule. Owner: Event Coordinator
5.7 Schedule load-in windows | Coordinate with the venue manager to assign each vendor a load-in time window that avoids conflicts with other vendors and the venue's own schedule. Owner: Event Coordinator Checkpoint: No two vendors are scheduled the same load-in window in a space that cannot fit both at once.
5.8 Confirm details before the event | Contact each vendor about a week before the event to reconfirm timing, final headcount or quantities, and any last details. Owner: Event Coordinator
5.9 Share the run sheet with vendors | Send each vendor the relevant sections of the event run sheet so they know their cues and timing on event day. Owner: Event Coordinator
5.10 Manage vendor issues on event day | Address vendor delays, substitutions or scope issues on event day by working with the event lead, following the event day run of show SOP. Owner: Event Coordinator
5.11 Process final payments | Confirm the vendor delivered per the scope of work before releasing the final payment, noting any shortfall before paying in full. Owner: Event Manager
5.12 Review vendor performance | Complete a vendor performance review after the event covering reliability, quality and communication, and update the preferred vendor list accordingly. Owner: Event Coordinator
6. Quality checks
Every vendor has a signed contract before a deposit is paid.
No two vendors share a conflicting load-in window in the same space.
Vendor delivery is confirmed against the scope of work before final payment.
A performance review is completed for every vendor used.
7. Records
Signed vendor contracts and scopes of work
Vendor payment tracker
Load-in schedule
Vendor performance review forms
8. KPIs
Percentage of vendors delivering per the agreed scope of work
Vendor payment schedule compliance
Load-in scheduling conflicts per event
Preferred vendor list retention rate
9. Common mistakes
Paying a vendor deposit before the contract is signed.
Scheduling two vendors into the same load-in window and space.
Not reconfirming details with vendors close to the event date.
Releasing final payment without confirming the vendor met the scope of work.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Alexa Uskova

## Training Log
Event Vendor Coordination SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Event Vendor Coordination SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Alexa Uskova

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.