## Checklist
MSP Client Onboarding Documentation SOP checklist
SOP-MSP-002 ¦ Rev 1.0 ¦ Owner: Onboarding Project Manager
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Hold the onboarding kickoff | The Onboarding Project Manager meets the client to confirm scope, timeline, go-live date, contacts and the list of information and access the MSP needs. | Onboarding Project Manager
5.2 | Collect access and existing documentation | The Client Point of Contact provides admin access, license and vendor details and any existing documentation, and introduces the MSP to the outgoing provider. Warning: Do not accept passwords by email or chat. Send a secure vault request link and have credentials entered there. | Client Point of Contact
5.3 | Take over and rotate admin credentials | The Onboarding Engineer changes every administrative password, stores the new ones in the client vault and enables MFA on admin accounts that lack it. Checkpoint: The outgoing provider’s accounts and remote tools are disabled on the agreed cutover date. | Onboarding Engineer
5.4 | Deploy monitoring and management agents | The Onboarding Engineer deploys the RMM agent and security tools to every server and endpoint and compares the agent count with the client’s expected device count. | Onboarding Engineer
5.5 | Run network and asset discovery | The Onboarding Engineer scans each site to find network devices, printers and other equipment that cannot run an agent, and records anything unexpected for review. | Onboarding Engineer
5.6 | Build the client documentation | The Onboarding Engineer creates the client hub from the standard template and documents sites, network, servers, cloud tenants, applications, backups and vendors. | Onboarding Engineer
5.7 | Assess the environment against standards | The Onboarding Engineer completes the baseline assessment, recording gaps such as missing MFA, failing backups, unsupported operating systems or open remote access. | Onboarding Engineer
5.8 | Agree the remediation plan | The Technical Account Manager prioritizes the baseline findings, estimates effort and agrees with the client which items are fixed in onboarding and which become projects. | Technical Account Manager
5.9 | Set up the client in the PSA | The Service Desk Lead configures the client’s contract, SLA, contacts, approvers, after-hours rules and ticket routing in the PSA. | Service Desk Lead
5.10 | Brief the service desk | The Service Desk Lead walks the technicians through the client hub, key runbooks, VIP users and known issues before the go-live date. | Service Desk Lead
5.11 | Tell client users how to get support | The Onboarding Project Manager sends the client’s staff a welcome guide explaining how to raise tickets, support hours and what to expect on go-live day. | Onboarding Project Manager
5.12 | Sign off onboarding | The Technical Account Manager reviews the onboarding checklist with the Client Point of Contact, records sign-off and moves the client to steady-state support. Checkpoint: Every checklist item is done, or open with an owner and due date that the client has accepted. | Technical Account Manager
Supervisor sign-off: |  |  | Date:

## SOP
MSP Client Onboarding Documentation SOP
Standard operating procedure
Document no. | SOP-MSP-002
Revision | 1.0
Owner | Onboarding Project Manager
Effective date | October 15, 2026
Review cycle | Every 12 months
1. Purpose
To onboard every new managed services client the same way, so the MSP takes control of the environment securely, documents it completely and hands the service desk everything it needs from day one.
2. Scope
Applies to the technical onboarding of every new managed services client, from the signed agreement to the start of steady-state support, including takeover from an outgoing IT provider. Commercial onboarding and billing setup are covered elsewhere.
Definitions
Outgoing provider | The previous IT provider or internal IT person who hands the environment over to the MSP.
Discovery | Scanning and inspecting the client environment to find every device, account, service and dependency.
Baseline assessment | A comparison of the client environment with the MSP’s technical standards, producing a list of findings and risks.
Go-live | The date the MSP’s service desk starts taking the client’s support requests under the agreement.
3. Responsibilities
Onboarding Project Manager | Runs the onboarding plan, timeline and kickoff, chases client inputs and owns the onboarding checklist until sign-off.
Onboarding Engineer | Takes over credentials, deploys agents, runs discovery and builds the client documentation.
Service Desk Lead | Sets up the client in the PSA and prepares the service desk to support the client from go-live.
Technical Account Manager | Reviews the baseline findings, agrees the remediation plan with the client and owns the relationship after go-live.
Client Point of Contact | Provides access, documents and contacts, coordinates with the outgoing provider and approves onboarding sign-off.
RACI matrix
Plan and run the onboarding kickoff | Onboarding Project Manager: R/A ¦ Onboarding Engineer: C ¦ Service Desk Lead: I ¦ Technical Account Manager: C ¦ Client Point of Contact: C
Take over and secure admin credentials | Onboarding Project Manager: A ¦ Onboarding Engineer: R ¦ Service Desk Lead: - ¦ Technical Account Manager: I ¦ Client Point of Contact: C
Discover and document the environment | Onboarding Project Manager: A ¦ Onboarding Engineer: R ¦ Service Desk Lead: I ¦ Technical Account Manager: C ¦ Client Point of Contact: C
Agree the remediation plan | Onboarding Project Manager: C ¦ Onboarding Engineer: C ¦ Service Desk Lead: - ¦ Technical Account Manager: R/A ¦ Client Point of Contact: C
Prepare the service desk for go-live | Onboarding Project Manager: A ¦ Onboarding Engineer: C ¦ Service Desk Lead: R ¦ Technical Account Manager: I ¦ Client Point of Contact: I
4. Materials and PPE
Materials, tools and systems
Onboarding checklist and project plan
Client documentation template set
Password manager with a new client vault
RMM tool and agent installers
Network discovery and scanning tool
PSA ticketing system
Baseline assessment checklist
5. Procedure
5.1 Hold the onboarding kickoff | The Onboarding Project Manager meets the client to confirm scope, timeline, go-live date, contacts and the list of information and access the MSP needs. Owner: Onboarding Project Manager
5.2 Collect access and existing documentation | The Client Point of Contact provides admin access, license and vendor details and any existing documentation, and introduces the MSP to the outgoing provider. Owner: Client Point of Contact Warning: Do not accept passwords by email or chat. Send a secure vault request link and have credentials entered there.
5.3 Take over and rotate admin credentials | The Onboarding Engineer changes every administrative password, stores the new ones in the client vault and enables MFA on admin accounts that lack it. Owner: Onboarding Engineer Checkpoint: The outgoing provider’s accounts and remote tools are disabled on the agreed cutover date.
5.4 Deploy monitoring and management agents | The Onboarding Engineer deploys the RMM agent and security tools to every server and endpoint and compares the agent count with the client’s expected device count. Owner: Onboarding Engineer
5.5 Run network and asset discovery | The Onboarding Engineer scans each site to find network devices, printers and other equipment that cannot run an agent, and records anything unexpected for review. Owner: Onboarding Engineer
5.6 Build the client documentation | The Onboarding Engineer creates the client hub from the standard template and documents sites, network, servers, cloud tenants, applications, backups and vendors. Owner: Onboarding Engineer
5.7 Assess the environment against standards | The Onboarding Engineer completes the baseline assessment, recording gaps such as missing MFA, failing backups, unsupported operating systems or open remote access. Owner: Onboarding Engineer
5.8 Agree the remediation plan | The Technical Account Manager prioritizes the baseline findings, estimates effort and agrees with the client which items are fixed in onboarding and which become projects. Owner: Technical Account Manager
5.9 Set up the client in the PSA | The Service Desk Lead configures the client’s contract, SLA, contacts, approvers, after-hours rules and ticket routing in the PSA. Owner: Service Desk Lead
5.10 Brief the service desk | The Service Desk Lead walks the technicians through the client hub, key runbooks, VIP users and known issues before the go-live date. Owner: Service Desk Lead
5.11 Tell client users how to get support | The Onboarding Project Manager sends the client’s staff a welcome guide explaining how to raise tickets, support hours and what to expect on go-live day. Owner: Onboarding Project Manager
5.12 Sign off onboarding | The Technical Account Manager reviews the onboarding checklist with the Client Point of Contact, records sign-off and moves the client to steady-state support. Owner: Technical Account Manager Checkpoint: Every checklist item is done, or open with an owner and due date that the client has accepted.
6. Quality checks
All administrative credentials were rotated and stored in the client vault before go-live.
Agent coverage matches the expected device count, with differences explained.
The client hub contains the full core documentation set at sign-off.
Baseline findings have an agreed owner, priority and plan.
The outgoing provider’s access was removed on the cutover date.
7. Records
Completed onboarding checklist with client sign-off
Baseline assessment report and remediation plan
Credential takeover log
Agent deployment and discovery results
8. KPIs
Days from signed agreement to go-live
Percentage of onboarding checklist items complete at go-live
Ticket volume and escalations in the first 30 days
Number of critical baseline findings closed within 90 days
9. Common mistakes
Going live before the outgoing provider’s access has been removed.
Accepting credentials over email and leaving them in the inbox.
Trusting the client’s device list instead of verifying it with discovery.
Skipping the service desk briefing, so the first tickets are worked blind.
10. Revision history
1.0 | Date: October 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Ilia Pirozhenko

## Training Log
MSP Client Onboarding Documentation SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
MSP Client Onboarding Documentation SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | October 15, 2026 | Initial release | Ilia Pirozhenko

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.