## Checklist
MSP Patch Management SOP checklist
SOP-MSP-006 ¦ Rev 1.0 ¦ Owner: Service Manager
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Agree patch windows with each client | The Technical Account Manager agrees each client’s maintenance windows, reboot rules and systems that need special handling, and records them in the client documentation. | Technical Account Manager
5.2 | Configure client patch policies in the RMM | The Patch Administrator sets up each client’s patch policies in the RMM to match the agreed windows, including third-party applications and a pilot group of devices. | Patch Administrator
5.3 | Review vendor releases each month | The Patch Administrator reviews the monthly vendor releases and known issues, and decides which patches to approve, defer or block. | Patch Administrator
5.4 | Patch the MSP’s own systems first | The Patch Administrator deploys the approved patches to the MSP’s internal devices first and watches for problems for at least one business day. | Patch Administrator
5.5 | Deploy to client pilot rings | The Patch Administrator releases the patches to the pilot group at every client in their next maintenance window and reviews the results and any tickets raised. | Patch Administrator
5.6 | Approve the broad rollout | The Service Manager reviews pilot results across clients and approves the broad rollout, or holds specific patches that caused problems. Checkpoint: No patch moves past the pilot rings without the Service Manager’s recorded approval. | Service Manager
5.7 | Deploy inside maintenance windows | The Patch Administrator lets the RMM deploy the approved patches to all remaining devices inside each client’s maintenance window, following the agreed reboot rules. | Patch Administrator
5.8 | Handle out-of-band critical patches | For an actively exploited vulnerability, the Service Manager authorizes out-of-band patching, and the Technical Account Manager tells affected clients before deployment. Warning: Even urgent patches go to a pilot group first, unless the Service Manager decides the risk of waiting is greater. | Service Manager
5.9 | Review patch compliance per client | After each cycle the Patch Administrator reviews the compliance report for every client and opens tickets for devices that failed, were offline or are pending a reboot. | Patch Administrator
5.10 | Fix devices that failed patching | The Service Desk Technician works each failed-device ticket: brings offline devices online, clears install errors, schedules reboots with users and confirms the patch installed. | Service Desk Technician
5.11 | Document patch exceptions | The Technical Account Manager records every device or patch that cannot be applied, with the reason, compensating controls and the client’s written acceptance of the risk. | Technical Account Manager
5.12 | Report patch status to the client | The Technical Account Manager reports compliance, exceptions and unsupported systems to the client each month and at every business review. | Technical Account Manager
Supervisor sign-off: |  |  | Date:

## SOP
MSP Patch Management SOP
Standard operating procedure
Document no. | SOP-MSP-006
Revision | 1.0
Owner | Service Manager
Effective date | October 15, 2026
Review cycle | Every 6 months
1. Purpose
To patch every managed client’s operating systems and third-party applications on a predictable schedule, inside agreed maintenance windows, with enough testing that a bad patch never reaches every client at once.
2. Scope
Applies to operating system, firmware and third-party application patches on servers and endpoints the MSP manages through its RMM tool. Network device firmware follows the same cadence but is scheduled as a change.
Definitions
Patch policy | The RMM settings that decide which patches are approved, when they install and how devices reboot for a client or device group.
Pilot ring | A small group of devices at each client that receives patches first, before the rest of the client’s devices.
Maintenance window | The agreed time when the MSP may install patches and reboot a client’s systems.
Out-of-band patch | A security patch released or deployed outside the normal monthly cycle because the risk cannot wait.
Patch exception | A device or patch deliberately excluded from patching, with a documented reason and the client’s acceptance of the risk.
3. Responsibilities
Patch Administrator | Maintains patch policies in the RMM, reviews vendor releases, runs the rings and produces compliance reports.
Service Manager | Approves the broad rollout each cycle, authorizes out-of-band patching and owns patch compliance across clients.
Service Desk Technician | Works tickets for devices that failed or missed patching and for user issues caused by a patch.
Technical Account Manager | Agrees maintenance windows and exceptions with each client and reports patch status at business reviews.
Client Point of Contact | Approves maintenance windows, names systems that need special handling and accepts the risk of exceptions.
RACI matrix
Agree maintenance windows and exceptions | Patch Administrator: C ¦ Service Manager: I ¦ Service Desk Technician: - ¦ Technical Account Manager: R/A ¦ Client Point of Contact: C
Maintain RMM patch policies | Patch Administrator: R ¦ Service Manager: A ¦ Service Desk Technician: - ¦ Technical Account Manager: I ¦ Client Point of Contact: -
Approve the broad rollout | Patch Administrator: C ¦ Service Manager: R/A ¦ Service Desk Technician: I ¦ Technical Account Manager: I ¦ Client Point of Contact: -
Remediate failed devices | Patch Administrator: C ¦ Service Manager: A ¦ Service Desk Technician: R ¦ Technical Account Manager: - ¦ Client Point of Contact: -
Report patch status to the client | Patch Administrator: C ¦ Service Manager: I ¦ Service Desk Technician: - ¦ Technical Account Manager: R/A ¦ Client Point of Contact: I
4. Materials and PPE
Materials, tools and systems
RMM tool with patch management
Third-party application patching catalog
Vendor release notes and security advisories
Client maintenance window register
Patch exception register
PSA ticketing system
Patch compliance report per client
5. Procedure
5.1 Agree patch windows with each client | The Technical Account Manager agrees each client’s maintenance windows, reboot rules and systems that need special handling, and records them in the client documentation. Owner: Technical Account Manager
5.2 Configure client patch policies in the RMM | The Patch Administrator sets up each client’s patch policies in the RMM to match the agreed windows, including third-party applications and a pilot group of devices. Owner: Patch Administrator
5.3 Review vendor releases each month | The Patch Administrator reviews the monthly vendor releases and known issues, and decides which patches to approve, defer or block. Owner: Patch Administrator
5.4 Patch the MSP’s own systems first | The Patch Administrator deploys the approved patches to the MSP’s internal devices first and watches for problems for at least one business day. Owner: Patch Administrator
5.5 Deploy to client pilot rings | The Patch Administrator releases the patches to the pilot group at every client in their next maintenance window and reviews the results and any tickets raised. Owner: Patch Administrator
5.6 Approve the broad rollout | The Service Manager reviews pilot results across clients and approves the broad rollout, or holds specific patches that caused problems. Owner: Service Manager Checkpoint: No patch moves past the pilot rings without the Service Manager’s recorded approval.
5.7 Deploy inside maintenance windows | The Patch Administrator lets the RMM deploy the approved patches to all remaining devices inside each client’s maintenance window, following the agreed reboot rules. Owner: Patch Administrator
5.8 Handle out-of-band critical patches | For an actively exploited vulnerability, the Service Manager authorizes out-of-band patching, and the Technical Account Manager tells affected clients before deployment. Owner: Service Manager Warning: Even urgent patches go to a pilot group first, unless the Service Manager decides the risk of waiting is greater.
5.9 Review patch compliance per client | After each cycle the Patch Administrator reviews the compliance report for every client and opens tickets for devices that failed, were offline or are pending a reboot. Owner: Patch Administrator
5.10 Fix devices that failed patching | The Service Desk Technician works each failed-device ticket: brings offline devices online, clears install errors, schedules reboots with users and confirms the patch installed. Owner: Service Desk Technician
5.11 Document patch exceptions | The Technical Account Manager records every device or patch that cannot be applied, with the reason, compensating controls and the client’s written acceptance of the risk. Owner: Technical Account Manager
5.12 Report patch status to the client | The Technical Account Manager reports compliance, exceptions and unsupported systems to the client each month and at every business review. Owner: Technical Account Manager
6. Quality checks
Every client has documented maintenance windows matched by its RMM patch policy.
Patches reached client pilot rings before any broad rollout.
Every device that failed or missed patching has a ticket.
Every patch exception has a reason and the client’s written risk acceptance.
Each client received a patch compliance report this month.
7. Records
Client maintenance window register
Monthly patch approval decisions
Patch compliance report per client
Patch exception register with client acceptance
8. KPIs
Patch compliance rate per client
Days to deploy critical security patches
Number of patch-related incidents per cycle
Number of open patch exceptions
9. Common mistakes
Approving every patch for every client at once with no pilot ring.
Patching outside the client’s agreed maintenance window.
Ignoring third-party applications and only patching the operating system.
Leaving unpatchable systems undocumented instead of recording an exception.
10. Revision history
1.0 | Date: October 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Ilia Pirozhenko

## Training Log
MSP Patch Management SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
MSP Patch Management SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | October 15, 2026 | Initial release | Ilia Pirozhenko

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.