## Checklist
Client Onboarding SOP checklist
SOP-ONB-002 ¦ Rev 1.0 ¦ Owner: Customer Success Manager
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Complete the sales-to-onboarding handoff | The account manager shares the signed contract, agreed scope, key contacts and any commitments made during the sales process with the implementation specialist before the kickoff call. Checkpoint: The handoff includes everything promised during the sale, so onboarding does not miss a commitment. | Account Manager
5.2 | Schedule the kickoff call | The implementation specialist schedules the kickoff call with the client contact within the agreed timeframe after contract signature, sharing an agenda in advance. | Implementation Specialist
5.3 | Run the kickoff call | The implementation specialist confirms the client's goals, timeline, key contacts and success criteria for onboarding, and agrees next steps with the client contact. | Implementation Specialist
5.4 | Gather detailed requirements | The implementation specialist sends the requirements questionnaire and works with the client contact to confirm configuration needs, integrations and any data to migrate. | Implementation Specialist
5.5 | Configure the account | The implementation specialist sets up the client's account, users and settings according to the confirmed requirements. | Implementation Specialist
5.6 | Migrate client data | The implementation specialist migrates the client's data using the data migration checklist and validates it against the client's source records for accuracy. Checkpoint: Migrated data is validated against the client's source records before training begins. | Implementation Specialist
5.7 | Train the client team | The implementation specialist runs training sessions for the client's team, covering core workflows and answering configuration-specific questions. | Implementation Specialist
5.8 | Run a pre-go-live review | The implementation specialist and client contact review the configured account together, confirming everything needed is in place before going live. Checkpoint: The client contact confirms in writing that the account is ready before go-live is scheduled. | Implementation Specialist
5.9 | Go live | The client begins using the product or service in their normal operations, with the implementation specialist available for immediate support in the days that follow. | Client Contact
5.10 | Monitor early usage | The customer success manager monitors usage and any support tickets in the first weeks after go-live, flagging any signs the client is struggling to adopt the product or service. | Customer Success Manager
5.11 | Hold the first milestone review | The customer success manager meets with the client contact to review progress against the original success criteria and agree on next steps or additional support. | Customer Success Manager
5.12 | Transition to ongoing account management | The customer success manager confirms onboarding is complete, documents any open items, and hands the account to its ongoing account management process. | Customer Success Manager
Supervisor sign-off: |  |  | Date:

## SOP
Client Onboarding SOP
Standard operating procedure
Document no. | SOP-ONB-002
Revision | 1.0
Owner | Customer Success Manager
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To move a new client from signed contract to live, successful use of the product or service, with a smooth handoff, clear setup steps and an early check that they are getting value.
2. Scope
Applies to new client accounts after a contract is signed, through go-live and the first milestone review. Ongoing account management after that point is covered by a separate process.
Definitions
Kickoff call | The first meeting with the client after the sales handoff, used to confirm goals, timeline and key contacts.
Go-live | The point at which the client is actively using the product or service in their normal operations.
Client contact | The primary person at the client organization responsible for the onboarding project on their side.
3. Responsibilities
Account Manager | Owns the sales-to-onboarding handoff and stays informed through go-live.
Implementation Specialist | Runs the kickoff, configures the account, migrates data and trains the client.
Client Contact | Provides requirements and data, coordinates their internal team, and confirms sign-off at each stage.
Customer Success Manager | Oversees the onboarding timeline, resolves blockers, and leads the first milestone review.
RACI matrix
Sales-to-onboarding handoff | Account Manager: R/A ¦ Implementation Specialist: I ¦ Client Contact: I ¦ Customer Success Manager: C
Run kickoff call and gather requirements | Account Manager: I ¦ Implementation Specialist: R/A ¦ Client Contact: R ¦ Customer Success Manager: C
Configure account and migrate data | Account Manager: - ¦ Implementation Specialist: R/A ¦ Client Contact: C ¦ Customer Success Manager: I
Train the client team | Account Manager: - ¦ Implementation Specialist: R/A ¦ Client Contact: R ¦ Customer Success Manager: I
Confirm go-live and first milestone review | Account Manager: I ¦ Implementation Specialist: C ¦ Client Contact: R ¦ Customer Success Manager: R/A
4. Materials and PPE
Materials, tools and systems
Signed contract and sales handoff notes
Onboarding project plan template
Requirements gathering questionnaire
Client account in the product or service platform
Training materials or client-facing guides
Data migration checklist
5. Procedure
5.1 Complete the sales-to-onboarding handoff | The account manager shares the signed contract, agreed scope, key contacts and any commitments made during the sales process with the implementation specialist before the kickoff call. Owner: Account Manager Checkpoint: The handoff includes everything promised during the sale, so onboarding does not miss a commitment.
5.2 Schedule the kickoff call | The implementation specialist schedules the kickoff call with the client contact within the agreed timeframe after contract signature, sharing an agenda in advance. Owner: Implementation Specialist
5.3 Run the kickoff call | The implementation specialist confirms the client's goals, timeline, key contacts and success criteria for onboarding, and agrees next steps with the client contact. Owner: Implementation Specialist
5.4 Gather detailed requirements | The implementation specialist sends the requirements questionnaire and works with the client contact to confirm configuration needs, integrations and any data to migrate. Owner: Implementation Specialist
5.5 Configure the account | The implementation specialist sets up the client's account, users and settings according to the confirmed requirements. Owner: Implementation Specialist
5.6 Migrate client data | The implementation specialist migrates the client's data using the data migration checklist and validates it against the client's source records for accuracy. Owner: Implementation Specialist Checkpoint: Migrated data is validated against the client's source records before training begins.
5.7 Train the client team | The implementation specialist runs training sessions for the client's team, covering core workflows and answering configuration-specific questions. Owner: Implementation Specialist
5.8 Run a pre-go-live review | The implementation specialist and client contact review the configured account together, confirming everything needed is in place before going live. Owner: Implementation Specialist Checkpoint: The client contact confirms in writing that the account is ready before go-live is scheduled.
5.9 Go live | The client begins using the product or service in their normal operations, with the implementation specialist available for immediate support in the days that follow. Owner: Client Contact
5.10 Monitor early usage | The customer success manager monitors usage and any support tickets in the first weeks after go-live, flagging any signs the client is struggling to adopt the product or service. Owner: Customer Success Manager
5.11 Hold the first milestone review | The customer success manager meets with the client contact to review progress against the original success criteria and agree on next steps or additional support. Owner: Customer Success Manager
5.12 Transition to ongoing account management | The customer success manager confirms onboarding is complete, documents any open items, and hands the account to its ongoing account management process. Owner: Customer Success Manager
6. Quality checks
Every commitment from the sales process is documented in the handoff before onboarding starts.
Migrated data is validated against source records before training.
The client contact confirms readiness in writing before go-live.
A milestone review happens within the agreed window after go-live.
7. Records
Sales handoff notes
Requirements questionnaire and configuration notes
Data migration validation results
Milestone review notes
8. KPIs
Time from contract signature to go-live
Percentage of onboarding milestones met on schedule
Client satisfaction score at the first milestone review
Support ticket volume in the first 30 days after go-live
9. Common mistakes
Starting the kickoff call without a complete sales handoff.
Migrating data without validating it against the client's source records.
Going live before the client confirms readiness.
Letting the account go quiet after go-live with no milestone review scheduled.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Alexa Uskova

## Training Log
Client Onboarding SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Client Onboarding SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Alexa Uskova

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.