## Checklist
Rental Unit Turnover SOP checklist
SOP-PRM-005 ¦ Rev 1.0 ¦ Owner: Property Manager
Completed by: |  |  | Date: |  |  | Shift:
Step | Task | Details | Owner | Done | Initials | Time | Notes
5.1 | Inspect the vacated unit | Walk the unit as soon as it's vacated, photographing the overall condition and comparing it against the tenant's move-out inspection notes. | Maintenance Technician
5.2 | Build the turnover scope | List every repair, replacement, and cleaning task needed to bring the unit to make-ready standard, and estimate the time and cost for each. | Maintenance Technician
5.3 | Get approval for the turnover budget | Submit the scope and estimated cost to the property manager for approval before ordering materials or scheduling contractors beyond routine repairs. | Property Manager
5.4 | Complete repairs and punch list items | Work through the punch list in a logical order, such as ceiling and wall repairs before flooring and painting before final cleaning. | Maintenance Technician
5.5 | Test all appliances and systems | Test the HVAC system, water heater, plumbing fixtures, and all appliances for proper operation, and address anything that fails before the unit is shown. Checkpoint: Every appliance and major system operates correctly when tested during the turnover. | Maintenance Technician
5.6 | Check and replace safety devices | Test smoke and carbon monoxide detectors, replace batteries, and confirm fire extinguishers and any required safety signage are present and current. Warning: Never leave a unit make-ready with a smoke or carbon monoxide detector that fails its test. | Maintenance Technician
5.7 | Repaint and refresh finishes | Patch and repaint walls where needed, and refresh worn finishes like cabinet hardware or caulking to a presentable, consistent standard. | Maintenance Technician
5.8 | Deep clean the entire unit | Deep clean every room, including inside appliances, cabinets, and closets, once repairs and painting are finished so dust and debris are fully removed. | Cleaning Contractor
5.9 | Change or rekey the locks | Change or rekey exterior locks and reset any electronic access codes so the previous tenant's keys or codes no longer work. Checkpoint: Locks or access codes are changed for every turnover before the unit is marked make-ready. | Maintenance Technician
5.10 | Run the make-ready inspection | Walk the finished unit against the make-ready checklist, photographing each room, and note any remaining item that needs to be fixed before approval. | Maintenance Technician
5.11 | Sign off on make-ready status | Review the completed checklist and photos, and mark the unit make-ready in the property management software so it can be listed and shown. | Property Manager
Supervisor sign-off: |  |  | Date:

## SOP
Rental Unit Turnover SOP
Standard operating procedure
Document no. | SOP-PRM-005
Revision | 1.0
Owner | Property Manager
Effective date | September 15, 2026
Review cycle | Every 12 months
1. Purpose
To turn a vacated unit around quickly and to a consistent make-ready standard, minimizing vacancy time while keeping the unit safe and presentable.
2. Scope
Applies to unit preparation between a tenant's move-out and the next tenant's move-in, including repairs, cleaning, and the make-ready inspection. Move-in and move-out procedures themselves are covered by separate SOPs.
Definitions
Make-ready | The status showing a unit has passed inspection and is ready to be shown or leased to a new tenant.
Turn | The full process of preparing a unit for a new tenant after the previous one moves out.
3. Responsibilities
Property Manager | Sets the turnover timeline, approves vendor costs, and signs off on the final make-ready inspection.
Maintenance Technician | Completes repairs, safety checks, and punch list items in the unit.
Cleaning Contractor | Performs the deep clean of the unit once repairs are complete.
RACI matrix
Inspect the vacated unit and scope work | Property Manager: I ¦ Maintenance Technician: R/A ¦ Cleaning Contractor: -
Complete repairs and punch list items | Property Manager: I ¦ Maintenance Technician: R/A ¦ Cleaning Contractor: -
Deep clean the unit | Property Manager: I ¦ Maintenance Technician: C ¦ Cleaning Contractor: R/A
Run safety and system checks | Property Manager: I ¦ Maintenance Technician: R/A ¦ Cleaning Contractor: -
Sign off on make-ready status | Property Manager: A ¦ Maintenance Technician: R ¦ Cleaning Contractor: I
4. Materials and PPE
Materials, tools and systems
Turnover scope and punch list template
Paint, flooring and fixture stock
Cleaning supplies and equipment
Smoke and carbon monoxide detector batteries
Make-ready inspection checklist
Camera or phone for before and after photos
Personal protective equipment
Work gloves
Dust mask for sanding or painting
Safety glasses
5. Procedure
5.1 Inspect the vacated unit | Walk the unit as soon as it's vacated, photographing the overall condition and comparing it against the tenant's move-out inspection notes. Owner: Maintenance Technician
5.2 Build the turnover scope | List every repair, replacement, and cleaning task needed to bring the unit to make-ready standard, and estimate the time and cost for each. Owner: Maintenance Technician
5.3 Get approval for the turnover budget | Submit the scope and estimated cost to the property manager for approval before ordering materials or scheduling contractors beyond routine repairs. Owner: Property Manager
5.4 Complete repairs and punch list items | Work through the punch list in a logical order, such as ceiling and wall repairs before flooring and painting before final cleaning. Owner: Maintenance Technician
5.5 Test all appliances and systems | Test the HVAC system, water heater, plumbing fixtures, and all appliances for proper operation, and address anything that fails before the unit is shown. Owner: Maintenance Technician Checkpoint: Every appliance and major system operates correctly when tested during the turnover.
5.6 Check and replace safety devices | Test smoke and carbon monoxide detectors, replace batteries, and confirm fire extinguishers and any required safety signage are present and current. Owner: Maintenance Technician Warning: Never leave a unit make-ready with a smoke or carbon monoxide detector that fails its test.
5.7 Repaint and refresh finishes | Patch and repaint walls where needed, and refresh worn finishes like cabinet hardware or caulking to a presentable, consistent standard. Owner: Maintenance Technician
5.8 Deep clean the entire unit | Deep clean every room, including inside appliances, cabinets, and closets, once repairs and painting are finished so dust and debris are fully removed. Owner: Cleaning Contractor
5.9 Change or rekey the locks | Change or rekey exterior locks and reset any electronic access codes so the previous tenant's keys or codes no longer work. Owner: Maintenance Technician Checkpoint: Locks or access codes are changed for every turnover before the unit is marked make-ready.
5.10 Run the make-ready inspection | Walk the finished unit against the make-ready checklist, photographing each room, and note any remaining item that needs to be fixed before approval. Owner: Maintenance Technician
5.11 Sign off on make-ready status | Review the completed checklist and photos, and mark the unit make-ready in the property management software so it can be listed and shown. Owner: Property Manager
6. Quality checks
Every turnover has a documented punch list closed out before make-ready sign-off.
Smoke and carbon monoxide detectors test working before the unit is marked make-ready.
Locks or access codes are changed on every turnover.
Make-ready photos show a fully cleaned, repaired unit matching the checklist.
7. Records
Turnover scope and punch list
Make-ready inspection checklist with photos
Vendor and material cost approvals
Lock rekey or access change log
8. KPIs
Average days from move-out to make-ready
Turnover cost per unit
Percentage of turnovers completed without a callback repair
9. Common mistakes
Marking a unit make-ready before testing all appliances and systems.
Forgetting to rekey locks or reset access codes after the previous tenant moves out.
Painting or cleaning before repairs are finished, causing rework.
Skipping the smoke and carbon monoxide detector test.
10. Revision history
1.0 | Date: September 15, 2026 ¦ Description: Initial release ¦ Reviewed by: Alexa Uskova

## Training Log
Rental Unit Turnover SOP training log
Record every employee trained on this SOP.
Employee name | Role | Date trained | Trainer | Employee signature | Trainer signature | Notes

## Revision Log
Rental Unit Turnover SOP revision log
Revision | Date | Description | Changed by | Approved by
1.0 | September 15, 2026 | Initial release | Alexa Uskova

## About
About this template
This checklist comes from the free SOP template library by Perfect Wiki.
Open the template page
Keep this SOP up to date where your team works
Add it to Perfect Wiki so your team can find it and ask questions about it in Microsoft Teams, Slack, kChat or Mattermost.
Add to Perfect Wiki
This is a template. Adapt it to your organization, equipment and local regulations before use.